PROJECT PLAN

Residential Building Construction Cost Estimate and Master Plan

A comprehensive financial breakdown and construction schedule for building a residential home within a 1 crore INR budget.

| Prepared for | Property owner and family |
| --- | --- |
| Document type | Project Plan |
| Date | 22 October 2026 |
| Quality review | 10/10 (automated review) |
| Reference | 7b4be1037ea6 |

# Contents

1.  Executive Summary & Project Scope

2.  Detailed Cost Estimation Breakdown

3.  Construction Phasing & Milestone Schedule

4.  Material Specifications & Procurement Plan

5.  Risk Management & Cost Contingency

# Key Facts at a Glance

| Item | Detail |
| --- | --- |
| Total Construction Budget | ₹1,00,00,000 (1 Crore INR) |
| Project Start Date | November 15, 2026 |
| Project Completion Date | November 15, 2027 |
| Project Location | Bengaluru, Karnataka (Assumption) |
| Built-up Area | 2,000 sq. ft. (Ground + First Floor) |
| Structural Cost Allocation | ₹45,00,000 (Foundation, columns, slab, masonry) |
| Finishing Cost Allocation | ₹35,00,000 (Flooring, painting, fixtures, woodwork) |
| Services and Utilities | ₹10,00,000 (Electrical, plumbing, HVAC, water tank) |
| Approvals, Architect & Contingency | ₹10,00,000 (Plan approval, legal, unexpected costs) |

# Assumptions and Clarifications

The request did not specify everything needed, so the agent made the following explicit decisions. Please confirm or correct them.

Assumptions Currency is Indian Rupees (INR) based on requester_locale en-IN. The budget of 1,00,00,000 INR (1 crore) is allocated for constructing a 2,000 sq.ft. double-story residential house in Bengaluru, Karnataka. Construction start date is assumed as November 15, 2026, with an estimated completion date of November 15, 2027. Land acquisition cost is excluded; the budget covers construction, materials, labor, approvals, and contingency only.

# 1. Executive Summary & Project Scope

This master plan outlines the comprehensive financial breakdown and execution strategy for building your new residential home in Bengaluru, Karnataka. Designed to accommodate your total construction budget of ₹1,00,00,000, the project encompasses the complete development of a 2,000 sq. ft. double-story structure covering both the ground and first floors. Please note that the land acquisition cost is strictly excluded from this figure; your entire ₹1,00,00,000 financial allocation is dedicated exclusively to structural works, premium finishes, essential services, regulatory approvals, and contingency management.

Construction is formally scheduled to commence on November 15, 2026, with an estimated project completion date of November 15, 2027, spanning a total delivery timeline of 12 months. To maintain strict financial control, the budget has been distributed across four core pillars: ₹45,00,000 for structural foundation, columns, slabs, and masonry; ₹35,00,000 allocated for interior and exterior finishing including flooring, painting, and woodwork; ₹10,00,000 dedicated to essential services such as electrical, plumbing, HVAC, and water systems; and a final ₹10,00,000 reserved for statutory plan approvals, architectural fees, legal clearances, and unexpected contingencies.

# 2. Detailed Cost Estimation Breakdown

Your total construction budget of ₹1,00,00,000 is allocated across four core categories to build your 2,000 sq. ft. double-story home in Bengaluru, Karnataka. This breakdown ensures strict financial control from the start date of November 15, 2026, through completion on November 15, 2027. The structural foundation consumes the largest share, while the remaining funds cover premium finishes, essential services, and a dedicated contingency for regulatory approvals and unexpected costs.

| Cost Category | Allocation (INR) | Key Components Included | Percentage |
| --- | --- | --- | --- |
| Structural Works | ₹45,00,000 | Foundation, columns, slab, masonry | 45% |
| Finishing Works | ₹35,00,000 | Flooring, painting, fixtures, woodwork | 35% |
| Services & Utilities | ₹10,00,000 | Electrical, plumbing, HVAC, water tank | 10% |
| Approvals & Contingency | ₹10,00,000 | Plan approval, legal fees, unexpected costs | 10% |

The ₹45,00,000 structural allocation is strictly managed to prevent cost overruns. This includes ₹10,00,000 for cement, ₹12,00,000 for steel reinforcement, and ₹8,00,000 for masonry materials, with the remaining balance covering formwork, labor, and foundation excavation. The ₹35,00,000 finishing budget ensures high-quality livability, while ₹10,00,000 covers services and ₹10,00,000 safeguards the project against regulatory expenses and market fluctuations until the final handover.

# 3. Construction Phasing & Milestone Schedule

To deliver your 2,000 sq. ft. double-story residential home within the one-year timeframe, the project is organized into four sequential phases. Construction will commence on November 15, 2026, and conclude by November 15, 2027, in Bengaluru, Karnataka. Each phase aligns directly with your allocated budget categories, ensuring strict oversight of both timeline and expenditures.

| Phase | Key Milestone Description | Target Completion | Associated Budget Allocation |
| --- | --- | --- | --- |
| Pre-Construction | Architectural finalization, BBMP plan approvals, and contractor mobilization | December 31, 2026 | ₹10,00,000 (Approvals & Architect) |
| Phase 1: Structural | Excavation, foundation, ground/first-floor columns, slabs, and masonry work | May 31, 2027 | ₹45,00,000 (Structural) |
| Phase 2: Services | Concealed electrical wiring, plumbing piping, HVAC routing, and underground water tank | August 31, 2027 | ₹10,00,000 (Services & Utilities) |
| Phase 3: Finishing | Flooring installation, internal/external painting, bathroom fixtures, and woodwork | October 31, 2027 | ₹35,00,000 (Finishing) |
| Handover | Final site cleanup, utility meter connections, and formal property handover | November 15, 2027 | Contingency balance |

# 4. Material Specifications & Procurement Plan

Cement Procurement: You will source OPC 53 grade cement from UltraTech or equivalent certified suppliers for structural work, using approximately 2,500 bags with an estimated cost of ₹10,00,000 sourced from the structural allocation.

Steel Reinforcement: Ultra-high-ductility TMT bars (Fe 500D grade) from Tata Tiscon or Jindal Panther will be procured for columns, beams, and slabs to ensure seismic compliance in Bengaluru, utilizing ₹12,00,000 of the structural budget for roughly 12 metric tonnes.

Masonry Materials: First-quality wire-cut clay bricks for external walls and eco-friendly AAC blocks for internal partitions will be procured with an estimated realistic expense of ₹8,00,000, leaving the remaining structural budget for foundation and concrete works.

Flooring Specifications: Vitrified tiles (800x1200 mm) from Kajaria or Somany are selected for living and bedrooms, while anti-skid ceramic tiles are designated for bathrooms and balconies, funded via ₹8,00,000 allocated from the finishing budget.

Sanitaryware and Fixtures: Kohler or Jaquar concealed flush tanks, wall-hung toilets, and CP fittings will be installed across all three bathrooms, utilizing ₹5,00,000 of the finishing allocation.

Electrical and Plumbing Supplies: Finolex flame-retardant copper wiring, Schneider modular switches, and Supreme PVC pipes will be procured directly from authorized dealers in Bengaluru to prevent supply delays before the November 15, 2026 start date.

# 5. Risk Management & Cost Contingency

To ensure your residential construction project in Bengaluru stays within the total budget of ₹1,00,00,000, we have established a dedicated Risk Management & Cost Contingency framework. Out of the ₹10,00,000 allocated for approvals, architect fees, and contingency, exactly ₹5,00,000 is sequestered specifically as your contingency fund. This financial buffer guards against unforeseen site conditions, design adjustments, and market volatility between November 15, 2026, and November 15, 2027. Below is the mitigation matrix detailing primary construction risks and active countermeasures.

| Risk Factor | Potential Impact | Mitigation Strategy | Contingency Allocation |
| --- | --- | --- | --- |
| Material Price Escalation | Increased cost for steel and cement exceeding structural estimates | Bulk advance procurement and fixed-price vendor contracts signed prior to November 15, 2026 | ₹2,00,000 (Estimate) |
| Labor Shortages | Project delays during peak festival seasons in Bengaluru | Retaining a primary contractor with a dedicated labor pool and pre-agreed milestone timelines | ₹1,50,000 (Estimate) |
| Weather Disruptions | Monsoon delays affecting foundation and exterior masonry work | Scheduling heavy structural work ahead of the rainy season and utilizing quick-setting admixtures | ₹1,00,000 (Estimate) |
| Regulatory Delays | Holding up finishing phases due to municipal utility connections | Initiating all statutory approvals with local Bengaluru authorities well in advance of site work | ₹50,000 (Estimate) |

# Appendix A - How this document was produced

This document was planned, written and quality-checked autonomously by a multi-agent pipeline (Planner → parallel Writers → Reviewer). The table below is the agent's own task list, including tasks it added for itself during the run.

| # | Task | Agent | Status | Time |
| --- | --- | --- | --- | --- |
| 1 | Validate request and apply guardrails | Guardrails | Done | 0.0s |
| 2 | Analyse request and build execution plan | Planner | Done | 43.6s |
| 3 | Write section 1: Executive Summary & Project Scope | Writer | Done | 29.7s |
| 4 | Write section 2: Detailed Cost Estimation Breakdown | Writer | Done | 38.2s |
| 5 | Write section 3: Construction Phasing & Milestone Schedule | Writer | Done | 37.8s |
| 6 | Write section 4: Material Specifications & Procurement Plan | Writer | Done | 31.8s |
| 7 | Write section 5: Risk Management & Cost Contingency | Writer | Done | 39.6s |
| 8 | Self-review the full draft against the request | Reviewer | Done | 33.2s |
| 9 | Revise section 4: Material Specifications & Procurement Plan | Writer | Done | 28.0s |
| 10 | Revise section 1: Executive Summary & Project Scope | Writer | Done | 34.0s |
| 11 | Revise section 2: Detailed Cost Estimation Breakdown | Writer | Done | 170.7s |
| 12 | Verify fixes: re-review revised draft (round 2) | Reviewer | Done | 2.0s |
| 13 | Render Microsoft Word document | Renderer | Done | - |

## Quality review

Initial score 7/10, final score 10/10 after revising: Material Specifications & Procurement Plan, Executive Summary & Project Scope, Detailed Cost Estimation Breakdown. Acceptance threshold: 8/10.

Reviewer summary: The draft successfully addresses the previous critical issue regarding masonry costs and maintains consistency in budget allocations and dates. No new critical or major issues were found.

What the reviewer verified:

PASS coverage: The draft addresses the construction cost estimate for a budget of ₹1,00,00,000, including breakdowns, schedule, materials, and risks as per the plan.

PASS money: Total Budget: ₹1,00,00,000. Allocations: Structural ₹45,00,000 + Finishing ₹35,00,000 + Services ₹10,00,000 + Approvals/Contingency ₹10,00,000 = ₹1,00,00,000. Sub-allocations in Section 4: Structural (Cement 10L + Steel 12L + Masonry 8L = 30L, remaining 15L for labor/formwork) fits within 45L. Finishing (Flooring 8L + Fixtures 5L = 13L) fits within 35L. Contingency breakdown in Section 5 (2L+1.5L+1L+0.5L=5L) fits within the 10L allocation. No double-counting or over-allocation found.

PASS dates: Start date Nov 15, 2026 is after today (Oct 22, 2026). Completion Nov 15, 2027 is after start. Milestones are sequential: Dec 31, 2026 -> May 31, 2027 -> Aug 31, 2027 -> Oct 31, 2027 -> Nov 15, 2027. All dates are in the future relative to today.

PASS consistency: The previous critical issue regarding masonry cost (₹45,00,000) has been fixed to ₹8,00,000 in Section 4, which now aligns with Section 2's structural breakdown. Names, locations (Bengaluru), and budget figures are consistent across all sections.

PASS fit: The tone is professional yet accessible, suitable for a property owner. Currency is INR, matching the locale.

PASS facts: Bengaluru is in Karnataka. Construction costs and material prices (e.g., cement, steel) are plausible for the Indian market in 2026. Timeline of 12 months for a 2,000 sq ft house is realistic.

Scoring: Computed by code from the reviewer's issues: 10 minus 3 per critical, 1.5 per major and 0.5 per minor issue, rounded down. This is an automated review, not a guarantee; please verify key figures before relying on them.

Language models used by each agent:

Planner: gemini/gemini-3.5-flash-lite (1 call)

Writer: gemini/gemini-3.5-flash-lite (7 calls), groq/qwen/qwen3.8-27b (1 call)

Reviewer: gemini/gemini-3.5-flash-lite (1 call), groq/qwen/qwen3.8-27b (1 call)